Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 15 July 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Book a Doctor – Online Doctor Appointment Booking System |
| Team Members | Anvesh Gudipalli (Team Lead), Kunasani Sravani, Parisi Rahul, Seelam Rukmini, Geethika Viri Mahitha Singidi |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a patient, I can register on the platform by entering my name, email, phone and password. | 3 | High | Kunasani Sravani |
| Sprint-1 |  | USN-2 | As a doctor, I can register on the platform with my name, email, specialization and consultation fee. | 3 | High | Parisi Rahul |
| Sprint-1 | Login | USN-3 | As a registered user, I can log in with my email and password and receive a JWT session token. | 2 | High | Seelam Rukmini |
| Sprint-1 | Doctor Search | USN-4 | As a patient, I can browse the list of approved doctors and search/filter by name or specialization. | 3 | High | Geethika Viri Mahitha Singidi |
| Sprint-2 | Doctor Profile | USN-5 | As a patient, I can view a doctor's detailed profile including specialization, fee and contact details. | 2 | High | Anvesh Gudipalli |
| Sprint-2 | Appointment Booking | USN-6 | As a patient, I can book an appointment with a doctor by selecting a date, time slot and reason for visit. | 5 | High | Kunasani Sravani |
| Sprint-2 |  | USN-7 | As a doctor, I receive a notification whenever a patient books a new appointment with me. | 2 | Medium | Parisi Rahul |
| Sprint-2 | Patient Dashboard | USN-8 | As a patient, I can view all my upcoming and past appointments with their current status. | 3 | High | Seelam Rukmini |
| Sprint-3 |  | USN-9 | As a patient, I can cancel an appointment that is still pending or confirmed. | 2 | Medium | Geethika Viri Mahitha Singidi |
| Sprint-3 | Document Upload | USN-10 | As a patient, I can upload medical documents against an appointment for the doctor to review. | 3 | Medium | Anvesh Gudipalli |
| Sprint-3 | Doctor Dashboard | USN-11 | As a doctor, I can view appointment requests from patients and update the status (confirm/complete/cancel). | 5 | High | Kunasani Sravani |
| Sprint-3 | Notifications | USN-12 | As a patient, I receive a notification whenever a doctor updates the status of my appointment. | 2 | Medium | Parisi Rahul |
| Sprint-4 |  | USN-13 | As a user, I can view all my notifications and mark them as read individually or all at once. | 2 | Low | Seelam Rukmini |
| Sprint-4 | Admin Approval | USN-14 | As an admin, I can review newly registered doctors and approve them before they appear in search results. | 3 | High | Geethika Viri Mahitha Singidi |
| Sprint-4 | Admin Dashboard | USN-15 | As an admin, I can view platform-wide statistics such as total users, doctors and appointments. | 3 | Medium | Anvesh Gudipalli |
| Sprint-4 | User Management | USN-16 | As an admin, I can view all registered users and deactivate an account if required. | 2 | Medium | Kunasani Sravani |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 11 | 6 Days | 01 Jul 2026 | 06 Jul 2026 | 11 | 06 Jul 2026 |
| Sprint-2 | 12 | 6 Days | 07 Jul 2026 | 12 Jul 2026 | 12 | 12 Jul 2026 |
| Sprint-3 | 12 | 6 Days | 13 Jul 2026 | 18 Jul 2026 |  |  |
| Sprint-4 | 10 | 6 Days | 19 Jul 2026 | 24 Jul 2026 |  |  |

Velocity:

Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per iteration unit (story points per day)

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts